## Sheet1
Tasks | Estimated hours | Sprint 1 hours | Sprint 2 hours | Sprint 3 hours | Sprint 4 hours | Sprint 5 hours | Sprint 6 hours | Sprint 7 hours | Sprint 8 hours | Sprint 9 hours | Sprint 10 hours | Sprint 11 hours | Sprint 12 hours | Sprint 13 hours | Sprint 14 hours | Sprint 15 hours | Sprint 16 hours | Total hours | Column1
idea | 100 | 32 | 32 | [14 empty] | 90
project planning | 5 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 8
project description | 10 | 0 | 0 | 20 | 8 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 38
burn down chart | 10 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2
gunt chart | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2
use case | 50 | 0 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 32
design | 20 |  |  |  | 0 | 8 |  |  |  |  | 11 | [6 empty] | 19
Domain model | 5 |  |  |  | 0 | 0 | 8 | [10 empty] | 8
class diagram | 20 |  |  |  |  | 0 |  | 8 | 10 | [8 empty] | 18
scenarios | 20 |  |  |  |  | 8 | 0 | [10 empty] | 8
sequense diagram | 80 | [5 empty] | 0 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 37
requirment | 20 |  |  |  | 8 |  |  | 0 |  |  |  | 0 | [5 empty] | 8
user stories | 10 |  |  |  | 8 |  |  | 0 | [9 empty] | 8
use case diagram | 20 |  |  |  | 0 |  |  | 0 | [9 empty] | 0
UP | 25 | [6 empty] | 0 |  |  |  | 8 | [5 empty] | 8
schedalling task in sql server | 30 | [6 empty] | 0 |  |  |  | 8 |  | 0 |  |  |  | 8
activity diagram | 40 |  |  |  |  | 8 | 8 |  | 0 |  |  | 0 | 0 |  |  |  |  | 16
EER- diagram | 10 | [6 empty] | 8 | 0 | 8 |  | 8 | [5 empty] | 24
Establish connection with SQL server, mongo cluster | 80 | [7 empty] | 0 | 8 |  |  | 0 |  |  |  |  | 8
conceptual diagram | 100 | [6 empty] | 8 | 0 | [8 empty] | 8
Implementing java extractor APP | 10 | [8 empty] | 8 |  |  |  | 10 |  |  |  | 18
Web App Auth. | 10 | [8 empty] | 0 |  |  | 16 |  |  |  |  | 16
implementing java extractor app | 10 | [8 empty] | 0 |  | 8 | [5 empty] | 8
MongoDB data structure | 10 | [9 empty] | 10 | [6 empty] | 10
triggers | 10 | [9 empty] | 0 |  |  | 20 |  |  |  | 20
testing DW | 10 | [9 empty] | 0 |  |  | 10 |  |  |  | 10
testing java extractor | 40 | [9 empty] | 0 |  |  | 10 |  |  |  | 10
testing webApp | 40 | [9 empty] | 0 |  |  | 10 |  |  |  | 10
testing webservices | 40 | [10 empty] | 0 |  | 10 |  |  |  | 10
web services controllers | 20 | [10 empty] | 0 | 0 | 10 | 0 | 0 | 8 | 18
schedalling firebase cloud | 20 | [10 empty] | 0 | [5 empty] | 0
refactor DW | 10 | [11 empty] | 0 |  |  |  |  | 0
Testing ETL | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 | 10
webservices class diagram | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 0 |  |  |  | 0 | 13
reviewing | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10 | 0 |  | 0 | 26
implementation | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 |  | 0 | 22
testing | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 |  | 70 | 0 | 0 | 81
scrum doc. | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
documentation | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 70 |  | 0 | 80
Actual remaining hours | 704 | 660 | 620 | 580 | 550 | 500 | 499 | 460 | 440 | 400 | 380 | 300 | 310 | 350 | 190 | 0 | 0
Estimated hours | 704 | 672 | 640 | 608 | 576 | 544 | 512 | 480 | 448 | 416 | 384 | 352 | 320 | 384 | 192 | 0 | 0